## PPAP_Checklist
SUPPLIER PPAP DOCUMENT SUBMISSION & TRACKING
Supplier | ABC Components Pvt. Ltd. |  | Revision | Rev A
Customer | XYZ Company |  | PPAP Level | Level 3
Part Name | Motor Mounting Bracket |  | Submission Date | 22-Aug-2026
Part Number | EMB-001 |  | Project Type | Simulated Academic Project
No. | PPAP Element | Required | Status | Document Reference | Remarks
1 | Design Records | Yes | Complete | Drawing_RevA | Verified
2 | Engineering Change Documents | Yes | Complete | ECN_001 | Verified
3 | Customer Engineering Approval | Yes | Complete | Approval_01 | Approved
4 | DFMEA | Yes | Complete | DFMEA_RevA | Verified
5 | Process Flow Diagram | Yes | Complete | PFD_RevA | Verified
6 | PFMEA | Yes | In Progress | PFMEA_RevA | Quality review pending
7 | Control Plan | Yes | Complete | CP_RevA | Verified
8 | MSA | Yes | In Progress | MSA_01 | GR&R pending
9 | Dimensional Results | Yes | Complete | DIM_001 | Pass
10 | Material / Performance Test | Yes | Complete | TEST_001 | Pass
11 | Initial Process Study | Yes | Not Started | — | Pending
12 | Laboratory Documentation | Yes | Complete | LAB_001 | Verified
13 | Appearance Approval | Yes | Complete | AAR_001 | Approved
14 | Sample Production Parts | Yes | Complete | SAMPLE_001 | Received
15 | Master Sample | Yes | Complete | MASTER_001 | Available
16 | Checking Aids | Yes | Complete | GAUGE_001 | Verified
17 | Customer-Specific Requirements | Yes | Complete | CSR_001 | Verified
18 | PSW | Yes | Not Started | — | Pending
PPAP Completion % | 77.78%
Pending Documents | 4
Completed Documents | 14
Rejected Documents | 0
Overall Status | PENDING

## Dashboard
SUPPLIER PPAP QUALITY DASHBOARD
Supplier | ABC Components Pvt. Ltd. |  | Part | Motor Mounting Bracket |  | PPAP Level | Level 3
PPAP Completion |  | Pending Documents |  | Completed Documents |  | Overall Status
77.78% |  | 4 |  | 14 |  | PENDING
Status | Count
Complete | 14
In Progress | 2
Not Started | 2
Rejected | 0
PRIORITY ACTION PLAN
Priority | Document | Issue | Recommended Action
High | Initial Process Study | Not Started | Request process capability study from supplier |  | Project Note: Data is simulated for an academic/portfolio demonstration.
High | PSW | Not Started | Request completed PSW for quality review
Medium | PFMEA | In Progress | Complete quality review and close comments
Medium | MSA | In Progress | Request GR&R / measurement study completion

## Instructions
HOW TO USE THIS PPAP TRACKER
1 | Open PPAP_Checklist and review the simulated supplier information.
2 | Use the Status dropdown for each PPAP element: Not Started, In Progress, Complete or Rejected.
3 | Update Document Reference and Remarks when the supplier submits or changes a document.
4 | The tracker automatically calculates completion %, pending documents, completed documents and overall status.
5 | Open Dashboard to view the supplier's PPAP status and priority action plan.
6 | Use this as a portfolio/academic project. The supplier data in this workbook is simulated.
7 | For an interview, explain that the purpose is to help a quality team identify missing PPAP submissions and prioritize follow-up.
Suggested interview explanation
I developed a simulated Excel-based PPAP Document Submission and Tracking Dashboard. The objective was to monitor the status of PPAP elements submitted by a supplier, identify missing or pending documents, calculate the completion percentage and create a priority action plan. I used Excel data validation, formulas, conditional formatting and charts to convert the supplier data into a simple decision-support tool for quality follow-up.